## To-do's and questions
Step | To do | Progress
Step 0 | Validate data and security | 30%
Step 1 | Authorize the Waldo app in the M365 tenant | 90%
Step 2 | Identify who will use the free or the complete version of Waldo | 30%
Step 3 | Order your licenses | 70%
Step 4 | Identify who will attend the Waldo administrator training | 30%
Step 5 | Schedule the administrator training for the first group | 30%
Step 6 | Identify the offices, the areas | 30%
Step 7 | Create the desks and the desk tags | 30%
Step 8 | Identify who can go where | 30%
Step 9 | Are there users with a disability? | 30%
Step 10 | Are there users who should always get the same desk, and no one else can reserve this desk? (fixed desks users) | 30%
Step 11 | Are there users who should get the same desk when they go to the office, but their desk can be reserved by someone else when they're not at the office? | 30%
Step 12 | Identify the preferred areas | 30%
Step 13 | Are there users who must have a specific equipment? | 30%
Step 14 | Tell users to set their favorite desks and nice-to-haves | 30%
Step 15 | Get details about the Work from hom policies. | 30%
Step 16 | Do you need the check-in feature?
Step 17 | Do you need unnumbered areas?
Step 18 | Improve the Outlook Smart Sync feature | 30%
Step 19 | Identify the offices owners and the IT people in charge of the set-up. | 30%
Step 20 | Request the map creation
Step 21 | Setup the office map | 30%
Step 22 | inform the IT support team | 30%
Step 23 | Adapt your onboarding process for new employees. | 30%
Step 24 | Communicate internally to the first group | 30%
Step 25 | Add Waldo to Microsoft Teams for the first group | 30%
Step 26 | Get feedback from the first group | 30%

## Define Offices and areas
office | area | unnumbered area | check-in | allow check-in until | process reservations until X days … | owners (area or office)
NEW-YORK | FINANCE | no | no | 11:00 | 10 | bob@hellowaldo.app
NEW-YORK | HR | no | no | 11:00 | 10 | Janice@hellowaldo.app
NEW-YORK | IT | no | no | 11:00 | 10 | Ted@hellowaldo.app
NEW-YORK | FREE | yes | no | 11:00 | 10 | emma@hellowaldo.app
Note on E1: We recommend to start with 11:00am.
Note on F1: We recommend to start with 10 days

## Define desks
desk | desk tag #1 | desk tag #2 | desk tag #3 | can only be reserved by
D1 | Double screen | Stand-up | Window nearby | bob@hellowaldo.app
D2 | Double screen | Window nearby
D3 | Double screen | Window nearby
D4 | Double screen | Window nearby

## Define parking spots
parking spaces | vehicle type | can only be reserved by | parking spot tag #1 | parking spot tag #2 | parking spot tag #3
P1 | car | emma@hellowaldo.app | reduced mobility | indoor
P2 | EV car |  | indoor
B1 | bike |  | indoor
B2 | bike |  | outdoor

## Identify Users
email | free or complete version | desk must-haves | area #1 | priority | area #2 | priority2 | area #3 | priority3 | area #4 | priority4 | parking reservation enabled | allowed parking types | parking must-haves | guest reservation
bob@helloaldo.app | complete | reduced mobility | finance | 1000 | HR | 100 |  |  |  |  | yes | car,EV car, bike | reduced mobility | yes
emma@helloaldo.app | complete |  | finance |  | HR |  | IT |  |  |  | yes | car,EV car, bike |  | yes
janice@hellowaldo.app | complete |  | finance |  | HR |  | IT |  |  |  | yes | car,EV car, bike |  | yes
ted@hellowaldo.app | complete |  | finance |  | IT | [5 empty] | no | bike |  | yes
harry@hellowaldo.app | free |  | free | [7 empty] | no |  |  | yes
Note on C1: Use must-haves cautiously. If Waldo can't find a desk with the same "must-have" (because it has already been reserved for someone else for example), Waldo will tell the user "sorry, there's no desk for you at the office".
Note on E1: We recommend to set high priority users with 1000 (0 equals no piority).