## Sheet1
Column1 | Documentation to read | Who's involved? | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7
Order the licenses | Documentation | Purchase department | bar: week 1
Consent the waldo app | Documentation | Microsoft 365 administrator | bar: week 1
Administrator training | Provided remotely by the Waldo team | The Waldo administrators (HR, IT, Facilites) | bar: week 2
The right questions to ask | Documentation | The Waldo administrators (HR, IT, Facilites) | bar: week 2
Configure Waldo | Documentation | The Waldo administrators (HR, IT, Facilites) | bar: week 3
Get your maps designed | Documentation | Usually, someone from facilities department request the design | bar: week 2 to week 3
Create the video | Documentation | Usually, someone from the HR department | bar: week 2 to week 3
Dry run | bar: week 4
Deploy the Waldo app | Documentation | Microsoft 365 administrator | bar: week 5 to week 6
Get feedback | Documentation | Usually, someone from the HR department | bar: week 7
As long as the licenses have not been orderd or the Waldo app has not consented to, you cannot move forward.
The design of your maps is done by the Waldo teams and it ususally takes 3-5 days to complete the design of a map. Please, take this into consideration when planning your project.